## Forward Traceability
Requirements | Tests | Executions | Defects
FKA-120 - As an HR admin user I want to be able to define details of sites and branches of the company. - 1 defect | FKA-124 - Verify that a location entry can be added in the 'Locations' list by filling required fields with valid data. | [CS] Admin Module - FAIL | FKA-128 - Backlog - [Add Location] 'Country' field value is not saved when using the keyboard to select it from the dropdown.
FKA-120 - As an HR admin user I want to be able to define details of sites and branches of the company. | FKA-125 - Verify that a location entry is not saved after clicking the 'Cancel' button in the 'Add Location' page. | [CS] Admin Module - PASS | None
FKA-120 - As an HR admin user I want to be able to define details of sites and branches of the company. - 1 defect | FKA-126 - Verify that a location can be searched by country in the 'Search' section of the 'Locations' page. | [CS] Admin Module - FAIL | FKA-129 - Backlog - [Locations Search] Locations cannot be searched by 'Country' when using the keyboard to select a value from the dropdown.
FKA-120 - As an HR admin user I want to be able to define details of sites and branches of the company. | FKA-127 - Verify that the 'Search' section of the 'Locations' page can be reset after filling all fields. | [CS] Admin Module - PASS | None
FKA-120 - As an HR admin user I want to be able to define details of sites and branches of the company. | FKA-130 - Verify that a locations entry can be deleted by clicking the trash icon. | [CS] Admin Module - PASS | None
FKA-120 - As an HR admin user I want to be able to define details of sites and branches of the company. | FKA-131 - Verify that a locations entry can be edited by replacing the required fields input with new valid values. | [CS] Admin Module - PASS | None
FKA-62 - As an HR admin user I want to be able to define work shifts. | FKA-101 - Verify that a work shift can be added by filling all fields with valid values. | [CS] Admin Module - PASS | None
FKA-62 - As an HR admin user I want to be able to define work shifts. - 1 defect | FKA-102 - Verify that mandatory fields on the 'Add Work Shift' page are marked with an asterisk symbol. | [CS] Admin Module - FAIL | FKA-114 - Backlog - [Add Work Shift] The mandatory 'Shift Name' text box is missing the asterisk symbol.
FKA-62 - As an HR admin user I want to be able to define work shifts. - 2 defect | FKA-105 - Verify that added work shifts are listed correctly in the 'Records found' section. | [CS] Admin Module - FAIL | FKA-118 - Backlog - [Work Shifts] The working hours are displayed as a 24H clock in the 'Records Found' section after being displayed as 12H clock in the 'Add Work Shift' section.
FKA-117 - Backlog - [Add Work Shift] The 'Duration Per Day' count does not show accurate minutes count.
FKA-61 - As an HR admin user I want to be able to define job categories. | FKA-97 - Verify that a job category name can be added by pasting it in the text box. | [CS] Admin Module - PASS | None
FKA-61 - As an HR admin user I want to be able to define job categories. | FKA-98 - Verify that a job category can be added by hitting the Enter case on the keyboard. | [CS] Admin Module - PASS | None
FKA-61 - As an HR admin user I want to be able to define job categories. | FKA-100 - Verify that after deleting all entries, 'Successfully Deleted' and 'No Records Found' notifications are displayed. | [CS] Admin Module - PASS | None
FKA-60 - As an HR admin user I want to be able to define employment status. | FKA-95 - Verify that the 'Name' text box in the 'Add Employment Status' section does not accept more than 50 characters. | [CS] Admin Module - PASS | None
FKA-60 - As an HR admin user I want to be able to define employment status. | FKA-96 - Verify that an employment status cannot be added when leaving text box blank. | [CS] Admin Module - PASS | None
FKA-60 - As an HR admin user I want to be able to define employment status. | FKA-99 - Verify that an employment status name cannot be edited when typing an existing value. | [CS] Admin Module - PASS | None
FKA-59 - As an HR admin user I want to be able to define pay grades. | FKA-91 - Verify the system's behavior when adding all currencies available to a pay grade. | [CS] Admin Module - PASS | None
FKA-59 - As an HR admin user I want to be able to define pay grades. | FKA-92 - Verify that a currency cannot be added by filling with invalid data. | [CS] Admin Module - PASS | None
FKA-59 - As an HR admin user I want to be able to define pay grades. | FKA-93 - Verify that all pay grades can be deleted at the same time. | [CS] Admin Module - PASS | None
FKA-59 - As an HR admin user I want to be able to define pay grades. | FKA-94 - Verify that added pay grades are listed in the 'Records found' section. | [CS] Admin Module - PASS | None
FKA-58 - As an HR admin user I want to be able to define job titles. | FKA-89 - Verify that a job title can be deleted by clicking the trash icon. | [CS] Admin Module - PASS | None
FKA-58 - As an HR admin user I want to be able to define job titles. | FKA-90 - Verify that a job title can be edited by replacing 'Name' text box with a new valid value. | [CS] Admin Module - PASS | None
FKA-58 - As an HR admin user I want to be able to define job titles. | FKA-86 - Verify that a job title cannot be added when job specification file is bigger than 1 MB. | [CS] Admin Module - PASS | None
FKA-58 - As an HR admin user I want to be able to define job titles. | FKA-87 - Verify that a job title can be added when all fields are filled. | [CS] Admin Module - PASS | None
FKA-58 - As an HR admin user I want to be able to define job titles. | FKA-88 - Verify that the user can cancel adding a job title when fields are not filled. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. | FKA-77 - Verify that a system user can be added by filling all fields. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. | FKA-78 - Verify that a system user cannot be added when exceeding the maximum number of characters on 'Username' text-box. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. - 1 defect | FKA-79 - Verify that a system user can be searched by 'Status'. | [CS] Admin Module - FAIL | FKA-113 - Backlog - [System Users Search] System users cannot be searched by 'Disabled' value.
FKA-57 - As an HR admin user I want to be able to administer users. | FKA-80 - Verify that the 'Search' section in the 'User Management' tab can be reset after filling all fields. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. | FKA-81 - Verify that a system user can be deleted by clicking on the checkbox next to the 'Username'. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. | FKA-82 - Verify that multiple system users can be deleted at the same time. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. - 1 defect | FKA-83 - Verify that the Orange HRM website is responsive. | [CS] Admin Module - FAIL | FKA-107 - Backlog - [User Management] 'Confirm Password' text is displayed without spacing under the password tips when viewing the responsive page.
FKA-57 - As an HR admin user I want to be able to administer users. | FKA-84 - Verify that the 'Add users' web page elements are aligned. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. | FKA-85 - Verify that a system user can be edited. | [CS] Admin Module - PASS | None
FKA-57 - As an HR admin user I want to be able to administer users. - 1 defect | FKA-106 - Verify the spacing between characters of 'Add User' page. | [CS] Admin Module - FAIL | FKA-108 - Backlog - [User Management] Two spaces instead of one are added between employee's first name and last name.